## Slide 1: SW Illinois Flood Prevention Project – Progress Report
June 23, 2011
Southwestern Illinois Council of Mayors

## Slide 2: River Elevation 6.23.2011

## Slide 3: SW Illinois Levee Systems
Designed and built in 1940’s and improved in ‘50s by Corps of Engineers as 500-year levees
Owned and maintained by Levee Districts
  Wood River Drainage and Levee District
  Metro-East Sanitary District
  Prairie DuPont Drainage and Levee District
  Fish Lake Drainage and Levee District
Owned and maintained by Corps
  Chain of Rocks Levee

## Slide 4
155,000 people
  40% minority
  21% low income
174 square miles
Longstanding and historic communities
  Alton
  Wood River
  Granite City
  East-St. Louis
  Columbia
  Dupo
  East Carondelet
  Collinsville

## Slide 5
Industrial core of the St. Louis region
55,000+ jobs
  Conoco – Phillips
  U.S. Steel
  Solutia
  Afton Chemical

## Slide 6: The Problem
Corps of Engineers identified Design Deficiencies that may compromise the “authorized level of protection” (52 + 2 feet on St. Louis gauge – approx. 500-year)
  Understanding of risk has improved
  Better design methods
  Increased design factor of safety post-Katrina
FEMA decides to de-accredit the levee system
“Fear, uncertainty, and doubt” about flood protection erodes the economic security of Metro-East

## Slide 7: Economic Impacts
Mandatory Flood Insurance
  $20 million/yr additional premiums for homeowners and businesses
  Another $30 million/yr for larger businesses
Building Standards
  Raise buildings above base flood elevation
Loss of Property Value
Negative Business Climate

## Slide 8: Opportunity
Resurgence of manufacturing
Intergovernmental success story
Renewed marketing opportunities

## Slide 9: Key Terms
Local levee owners (or the Corps) must certify that levee systems will meet federal standards for protecting from a flood with a probability of 1% likelihood of occurring in one year (100-year flood).
FEMA accredits levee systems that have been certified to meet federal standards.

## Slide 10: Progress…
FEMA announces deaccreditation – August 2007
Haine introduces legislation to impose tax and create Flood Prevention Districts – November 2007
Illinois Flood Prevention District Act signed into law – May 2008

## Slide 11: Progress…
County FPDs are appointed – June 2008
Tax approved by county boards - July-Sept 2008
Tax collections start – January 2009
Corps concludes project to be finished in 2044 – May 2009
Intergovernmental Agreement signed June 2009
First meeting of FPD Council – June 2009
FPD staff hired – July 2009
Authorize challenge of FIRMS – August 2009

## Slide 12: Progress…
Select financial advisor – September 2009
Adopt project strategy – September 2009
Begin levee inspection – December 2009
Select consultants for design competition – December 2009
Issue RFP for design competition – February 2010
Select design consultants – June 2010
Begin design process - 2010

## Slide 13: Progress…
File suit against FEMA – November 2010
Issue $94 million in bonds – November 2010
Progress set of construction drawings – March 2011
30% design drawings – May 2011
Project implementation plan – June 2011
60% design drawings – December 2011
Construction begins – 1st Qtr. 2012 ?

## Slide 14: Our goal…
Finish improvement of levee systems in three counties at a cost of about $160 million in five years (2015) or less
Limit economic hardship during the time that flood protection is being improved

## Slide 15: Design Progress

## Slide 16
Scale: None
Drawn by: MG
Date: March 16, 2011
AMEC File No. 5-6317-0001
LEVEE ILLUSTRATION
Levee
Aquifer
Semi-pervious Blanket
Aquifer
Semi-pervious Blanket
Levee

## Slide 17
Scale: None
Drawn by: LS
Date: March 16, 2011
AMEC File No. 5-6317-0001
WOOD RIVER
PLANS AND CROSS SECTIONS
CUTOFF WALLS- Narrow slots filled with slurry.
BEDROCK
DEEP CUTOFF WALLS-Penetrate through the aquifer to bedrock
SHALLOW CUTOFF WALLS-Partially penetrate the aquifer

## Slide 18
Scale: None
Drawn by: LS
Date: March 16, 2011
AMEC File No. 5-6317-0001
WOOD RIVER
PLANS AND CROSS SECTIONS
SEEPAGE BERM
Adds weight to landside surface.
Abuts the levee.
Slopes away from levee.
SOIL FILL IN LOW SPOTS
Raises land surface.
Used to fill in ditches, borrow pits etc.
May not abut the levee.

## Slide 19
Scale: None
Drawn by: LS
Date: March 16, 2011
AMEC File No. 5-6317-0001
WOOD RIVER
PLANS AND CROSS SECTIONS
T-TYPE RELIEF WELLS
Water flows from the relief well to a collector pipe below ground.
Collector connects several relief wells
D-TYPE RELIEF WELLS
Water flows directly from the relief well.

## Slide 25: Uncertainties
Permitting
Certification of levees owned or improved by the Corps
Weather
Financial markets
Costs

## Slide 26: Need more information?
www.floodpreventiondistrict.org
Les Sterman
les@floodpreventiondistrict.org
618-343-9120

## Slide 27: Questions/ Comments/ Suggestions?